## Slide 1: Six areas to take forward
The August strategy review, grouped into workstreams.
The first four cover the eleven tracked actions; ALP and LIA are open lanes still to be scoped.
Area | Actions | Outcome | Stage progress | Finance
AI content optimisation | T1–T4 | CTR, impressions | Open — none started | TBC
Conversational attributes | T6, T7, T10 | Cross-sell, AOV, AI citations | Open — none started | TBC
Overlay services | T9, T11 | CTR, CVR | In test — Social mock-up shared, Shopping overlay trialling | TBC
Keyword & peak planning | T5, T8 | CVR, CTR | Awaiting promo calendar from EM | TBC
ALP — landing pages | — | Dwell, CVR | Not scoped | TBC
LIA reactivation | — | Store visibility | Open lane — store-ID work outstanding | TBC